## Sheet1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Completing the "index.html" (HTML) | 7 | 8 | 8 | 0 | Philipp
Prototype of the Login & Family Setup Menu | 5 | 5 | 5 | 0 | Philipp
Supplementary Pages (About us, School) | 6 | 6 | 6 | 0 | Alex
Improving the Supplementary pages coded by alex | 8 | 9 | 9 | 0 | Philipp
Translation Work on "start.html" | 5 | 5 | 5 | 0 | Philipp & Alex
Translation Work on "us.html" | 6 | 6 | 0 | 6 | Alex
Register and Login form development | 10 | 11 | 11 | 0 | Philipp
Developing "creation.html" | 10 | 6 | 6 | 0 | Philipp
Beeing able to create a family group + database (json) | 15 | 15 | 5 | 10 | Philipp